## Document Register
DOCUMENT REGISTER
Company: Armax Engineering Ltd |  |  |  |  | Project: Infrastructure Development 2026 |  |  |  |  | Rev: A
Doc No. | Title | Discipline | Doc Type | Rev | Status | Date Issued | Author | Reviewed By | Approved By | File Path | Remarks
AEL-ENG-SOP-001-A | Document Control Procedure | Enginnering | SOP | A | Approved | 2025-01-10 | A. Harald | M. Joshua | T. Shugz | \Docs\Engineering\SOP\AEL-ENG-SOP-001-A.pdf | Initial Issue
AEL-ENG-DRW-002-B | Site Lay-out Drawing - Phase 1 | Engineering | Drawing | B | Issued for Construction | 2025-02-02 | J. Ben | M. Joshua | T. Shugz | \Docs\Engineering\Drawings\AEL-ENG-DRW-002-B.pdf | Rev B supersedes Rev A
AEL-HSE-POL-001-A | Health & Safety Policy | HSE | Policy | A | Approved | 2025-01-15 | C.Gerald | S. Hazeed | T. Shugz | \Docs\HSE\Policies\AEL-HSE-POL-001-A.pdf | Annual review due Jan 2027
AEL-QA-WI-003-A | Inspection & Test Work Instruction | Quality | Work Instruction | A | Under Review | 2025-03-20 | O. Kenneth | S. Hazeed | T. Shugz | op0- | Pending approval
AEL-ENG-RPT-004-A | Geotechnical Survey report | Engineering | Report | A | Approved | 2025-02-28 | Z. Hassan | M. Joshua | T. Shugz | \Docs\Engineering\Reports\AEL-ENG-RPT-004-A | External consultant report
AEL-COM-LTR-005-A | Client Correspondence -Q1 2026 | Commercial | Letter | A | Issued for Construction | 2025-03-01 | M.Kazim | T. Shela | T. Shugz | \Docs\Commercial\Letters¦AEL-COM-LTR-005-A | Sent to client
AEL-HSE-FORM-006-A | Incident Report Form | HSE | Form | A | Approved | 2025-01-20 | E. Molan | S. Hazeed | T. Shugz | \Docs\HSE\Forms\AEL-HSE-FORM-006-A | Master form- do not alter
AEL-ENG-SPEC-007-A | Technical Specification - Concrete Works | Engineering | Specification | A | Draft | 2025-04-01 | B. Rasheed |  |  | \Docs\Engineering\Specs\AEL-ENG-SPEC-007-A | Work in progress

## Instructions
DOCUMENT REGISTER- INSTRUCTIONS
HOW TO USE THIS REGISTER
1. Enter each document on a new row starting from row 4.
2. Use the Document Numbering System (see campanion document) to assign Doc No.
3. Click the Status dropdown in column F to select the document status.
4. Update the File Path column with the exact location of the saved document.
5. Use the filter arrows in row 3 to filter discipline, status, author, etc.
STATUS DEFINITION
.
Under Review - Document has been submitted for review/approval.
Approved - Document has been reviewed and approved internally.
Issued for Construction - Final approved document issued to site/client.
Superseded - A newer revision has replaced this document.
Void - Document has been cancelled and is no longer valid.